## Sheet1
Story Ref # | Priority | Feature | Story Title | As A(n) | I Want To | So That | Acceptance Criteria | Story Points | Release Plan
1 |  | Property Management | Story 1 | Admin | manage the property database | properties can be created, updated or removed. | Add, edit and delete properties from the database | 32 | 2
2 |  | View Property | Story 2 | General User | view available properties | I can choose the best fit. | At least 25 per page. Ideally Never ending scroll | 16 | 4
3 |  | Search Properties | Story 3 | General User | Apply constraints to list of properties | I can differentiate similiar properties | Search by bedrooms | 16 | 3
4 |  | Staff Contact Information | Story 4 | General User | have access to staff contact details | I can contact them if with enquiries | Phone numbers, emails and picture of staff member | 4 | 1
5 |  | User Contact Information | Story 5 | Staff Member | have access to tenant and home owner contact details | I can contact them as necessary | Phone number for both tenant and home owner. | 4 | 1
6 |  | Website Accounts | Story 6 | User | be able to create an account | access secure information | Create base level account - upgradeable by David | 4 | 2
7 |  | Account Priviliges | Story 7 | Admin | assign different access levels | privileges are specifically assigned | Account levels for admin, staff, tenants and homeowners. | 8 | 2
8 |  | Clear Interface | Story 8 | General User | be able to clearly read all information on the site | information is easy to read and clear | Objectively pleasing to the eye and tidy | 8 | 1
9 |  | View Property Pictures | Story 9 | General User | be able to see a picture(s) of the property | identify the best property | Single picture available for each image | 4 | 1
10 |  | Add properties | Story 10 | Homeowner | add properties that are available for rent | I can expand my portfolio |  | 8 | 4
11 |  | Edit Properties | Story 11 | Homeowner | edit or remove properties available for rent | I can improve or reduce my portfolio |  | 4 | 4
12 |  | Sort Properties | Story 12 | General User | sort the properties by key details | compare similiar properties after searching |  | 16 | 3
13 |  | Lease Durations | Story 13 | Staff Member | view the current duration of active leases | plan future tenants and renewals. |  | 4 | 5
14 |  | Property Approval | Story 14 | David | have to approve new properties added by homeowners | the site remains free of spam |  | 4 | 4
15 |  | Inspection Booking | Story 15 | General User | be able to view and book an inspection time | I am able to view a property before renting |  | 2 | 5